## Overview (hidden)
| Monday 5/11 | [5 empty] | Tuesday 5/12 | [13 empty] | Wednesday 5/13 | [14 empty] | Thursday 5/14 | [12 empty] | Friday 5/15 | [12 empty] | Saturday 5/16 | [13 empty] | Sunday 5/17 | [11 empty] | Monday 5/18
| 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00 | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 16:15 | 17:00 | 18:00 | 19:00 | 19:15 | 8:00 | 9:00 | 9:15 | 10:00 | 11:00 | 12:00 | 13:00 | 13:15 | 14:00 | 15:00 | 16:00 | 17:00 | 17:15 | 18:00 | 19:00 | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 12:15 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00 | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 16:15 | 17:00 | 18:00 | 19:00 | 8:00 | 9:00 | 10:00 | 10:15 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 15:15 | 16:00 | 17:00 | 18:00 | 19:00 | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00 | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00
SYN-PERSON-001 | Ready for CAB | [11 empty] | CAB | [6 empty] | Verification Call | [59 empty] | Verification call ready for Prod | [7 empty] | Available for User Issues
SYN-PERSON-002 | [32 empty] | Verification Call | [7 empty] | Verification call | [16 empty] | Validation Call
SYN-PERSON-003 | [20 empty] | Deploy Appian Code | [6 empty] | Verification Email | Verify Integration and Load Balancing | [12 empty] | Defect Remediation | [6 empty] | Import Users | [12 empty] | Verify LDAP |  |  | Verification Email
SYN-PERSON-004 | [13 empty] | Deploy and Secure ESB | [53 empty] | Point to FXI 5.2 |  |  | Verification Email
SYN-PERSON-005 | [58 empty] | Facets Upgrade
SYN-PERSON-006 | [13 empty] | Deploy VC |  | Verification Email
SYN-PERSON-007 | [35 empty] | Post Implementation Testing |  |  |  |  | Verification call | Open Bridge line for defect resolution
SYN-PERSON-008 | [35 empty] | Identify Users |  |  |  |  | Verification call
SYN-PERSON-009 | [71 empty] | Point to FXI 5.2 |  |  |  | System Available to BPI team
SYN-PERSON-010 | [20 empty] | Identify Target Machines | [27 empty] | Deploy IE 11 to end user desktops

## Cover Page
Information Solutions (IS) Methodology Deployment Playbook Template Revision Date: June 28, 2024
Project: Salesforce Marketing Cloud Email Campaign Tracking Details Ingestion into Lakehouse
Project Manager:
Portfolio Director:
Multiple workstreams present:
Revision history
Date | Version | Author(s) | Description of Version/Changes
2026-08-11 | 1 | SYN-PERSON-011 | As part of this RFC, we are deploying below changes : 1. Ingestion of IIG metadata entries for SFMC

## PrePost-Prod & Prod Execution
| MANDATORY | OPTIONAL | MANDATORY | [12 empty] | OPTIONAL | MANDATORY
# | Task | Task Detail | RFC#s | Deployment Team | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Planned Start Time | Planned End Time | Actual Start Time | Actual End Time | Task Owner | Status | Task Dependency | Task Instructions | Comments: Touch Point Calls/Emails
PRE-PRODUCTION
PRODUCTION
1 | Take back-up of the IIG tables | Enviroment Details : Virtual Machine: SYN-VM-001 Server Name: syn-sqlserver-001.synthetic.example CREATE TABLE pr_dlk.backup_prod.DATA_FACTORY_PIPELINE_SCHEDULE_bkp_SYN-RFC-002 AS SELECT * FROM pr_dlk_adb.dbo.DATA_FACTORY_PIPELINE_SCHEDULE; CREATE TABLE pr_dlk.backup_prod.ADLS_DELTA_INGESTION_DETAILS_bkp_SYN-RFC-002 AS SELECT * FROM pr_dlk_adb.dbo.ADLS_DELTA_INGESTION_DETAILS; CREATE TABLE pr_dlk.backup_prod.STGDELTA_STDDELTA_INGESTION_DETAILS_bkp_SYN-RFC-002 AS SELECT * FROM pr_dlk_adb.dbo.STGDELTA_STDDELTA_INGESTION_DETAILS; CREATE TABLE pr_dlk.backup_prod.DATABRICKS_NOTEBOOK_DETAILS_bkp_SYN-RFC-002 AS SELECT * FROM pr_dlk_adb.dbo.DATABRICKS_NOTEBOOK_DETAILS; CREATE TABLE pr_dlk.backup_prod.EMAIL_TEMPLATE_CONFIG_bkp_SYN-RFC-002 AS SELECT * FROM pr_dlk_adb.dbo.EMAIL_TEMPLATE_CONFIG; CREATE TABLE pr_dlk.backup_prod.ALL_FILES_STATIC_INFORMATION_bkp_SYN-RFC-002 AS SELECT * FROM pr_dlk_adb.dbo.ALL_FILES_STATIC_INFORMATION; CREATE TABLE pr_dlk.backup_prod.DATA_QUALITY_RULES_bkp_SYN-RFC-002 AS SELECT * FROM pr_dlk_adb.dbo.DATA_QUALITY_RULES; INSERT INTO pr_dlk.backup_prod.backup_creation_log ( DATA_LAYER, MAIN_TABLE_CATALOG, MAIN_TABLE_SCHEME, MAIN_TABLE_NAME, BACKUP_TABLE_NAME, APPLICATION, TICKET_ID, DEPLOYMENT_DATE, RETENTION_PERIOD_IN_DAYS, LAST_DATE_OF_RETENTION, DELETION_STATUS, TICKET_CREATED_BY, BACKUP_DELETED_DATE, BACKUP_DELETED_BY, BACKUP_CREATED_DATE, BACKUP_CREATED_BY, UPDATED_DATE, UPDATED_BY) VALUES ('IIG','pr_dlk_adb','dbo','DATA_FACTORY_PIPELINE_SCHEDULE','pr_dlk.backup_prod.DATA_FACTORY_PIPELINE_SCHEDULE_bkp_SYN-RFC-002','SFMC','RFC#SYN-RFC-001','2026-08-20',30,'2026-09-20','N','syn-user-001-RFC#SYN-RFC-001',NULL,NULL,CURRENT_TIMESTAMP,'syn-user-001-RFC#SYN-RFC-001',CURRENT_TIMESTAMP,'syn-user-001-RFC#SYN-RFC-001'), ('IIG','pr_dlk_adb','dbo','ADLS_DELTA_INGESTION_DETAILS','pr_dlk.backup_prod.ADLS_DELTA_INGESTION_DETAILS_bkp_SYN-RFC-002','SFMC','RFC#SYN-RFC-001','2026-08-20',30,'2026-09-20','N','syn-user-001-RFC#SYN-RFC-001',NULL,NULL,CURRENT_TIMESTAMP,'syn-user-001-RFC#SYN-RFC-001',CURRENT_TIMESTAMP,'syn-user-001-RFC#SYN-RFC-001'), ('IIG','pr_dlk_adb','dbo','STGDELTA_STDDELTA_INGESTION_DETAILS','pr_dlk.backup_prod.STGDELTA_STDDELTA_INGESTION_DETAILS_bkp_SYN-RFC-002','SFMC','RFC#SYN-RFC-001','2026-08-20',30,'2026-09-20','N','syn-user-001-RFC#SYN-RFC-001',NULL,NULL,CURRENT_TIMESTAMP,'syn-user-001-RFC#SYN-RFC-001',CURRENT_TIMESTAMP,'syn-user-001-RFC#SYN-RFC-001'), ('IIG','pr_dlk_adb','dbo','DATABRICKS_NOTEBOOK_DETAILS','pr_dlk.backup_prod.DATABRICKS_NOTEBOOK_DETAILS_bkp_SYN-RFC-002','SFMC','RFC#SYN-RFC-001','2026-08-20',30,'2026-09-20','N','syn-user-001-RFC#SYN-RFC-001',NULL,NULL,CURRENT_TIMESTAMP,'syn-user-001-RFC#SYN-RFC-001',CURRENT_TIMESTAMP,'syn-user-001-RFC#SYN-RFC-001'), ('IIG','pr_dlk_adb','dbo','EMAIL_TEMPLATE_CONFIG','pr_dlk.backup_prod.EMAIL_TEMPLATE_CONFIG_bkp_SYN-RFC-002','SFMC','RFC#SYN-RFC-001','2026-08-20',30,'2026-09-20','N','syn-user-001-RFC#SYN-RFC-001',NULL,NULL,CURRENT_TIMESTAMP,'syn-user-001-RFC#SYN-RFC-001',CURRENT_TIMESTAMP,'syn-user-001-RFC#SYN-RFC-001'), ('IIG','pr_dlk_adb','dbo','ALL_FILES_STATIC_INFORMATION','pr_dlk.backup_prod.ALL_FILES_STATIC_INFORMATION_bkp_SYN-RFC-002','SFMC','RFC#SYN-RFC-001','2026-08-20',30,'2026-09-20','N','syn-user-001-RFC#SYN-RFC-001',NULL,NULL,CURRENT_TIMESTAMP,'syn-user-001-RFC#SYN-RFC-001',CURRENT_TIMESTAMP,'syn-user-001-RFC#SYN-RFC-001'), ('IIG','pr_dlk_adb','dbo','DATA_QUALITY_RULES','pr_dlk.backup_prod.DATA_QUALITY_RULES_bkp_SYN-RFC-002','SFMC','RFC#SYN-RFC-001','2026-08-20',30,'2026-09-20','N','syn-user-001-RFC#SYN-RFC-001',NULL,NULL,CURRENT_TIMESTAMP,'syn-user-001-RFC#SYN-RFC-001',CURRENT_TIMESTAMP,'syn-user-001-RFC#SYN-RFC-001'); | SYN-RFC-001 | SYN-PERSON-012 | 2026-08-20 | 2026-08-20 |  |  | 2:30:00 PM IST | 06:30 PM IST |  |  | SYN-PERSON-011 |  | None
2 | Copy SFMC_IIG.xlsx to ADLS raw location | Copy SFMC_IIG.xlsx to ADLS raw location. Enviroment Details to ADLS raw location: Target Storage account: synstorageacct001 Target container name: SYN-RESOURCE-001 Target Directory: /Temp File Location:O:\\SYN-INTERNAL-SHARE\\001 Documentation\2026_3_QTR_Release\SYN-RFC-001_SFMC\'' If the subfolder do not exist, please create it | SYN-RFC-001 | SYN-PERSON-012 | 2026-08-20 | 2026-08-20 |  |  | 2:30:00 PM IST | 06:30 PM IST |  |  | SYN-PERSON-011 |  | None
3 | Execute Pipeline to insert entries into IIG Tables | Enviroment Details : Data Factory : SYN-RESOURCE-002 Pipeline Name: IIG-METADATA-PIPELINE insert all entries into respective tables (table names are mentioned as sheet names as well) from the file - SFMC_IIG.xlsx DATA_FACTORY_PIPELINE_SCHEDULE:DATA_FACTORY_PIPELINE_SCHEDULE ADLS_DELTA_INGESTION_DETAILS:ADLS_DELTA_INGESTION_DETAILS STGDELTA_STDDELTA_INGESTION_DET:STGDELTA_STDDELTA_INGESTION_DETAILS DATABRICKS_NOTEBOOK_DETAILS:DATABRICKS_NOTEBOOK_DETAILS EMAIL_TEMPLATE_CONFIG:EMAIL_TEMPLATE_CONFIG ALL_FILES_STATIC_INFORMATION:ALL_FILES_STATIC_INFORMATION DATA_QUALITY_RULES:DATA_QUALITY_RULES | SYN-RFC-001 | SYN-PERSON-012 | 2026-08-20 | 2026-08-20 |  |  | 2:30:00 PM IST | 06:30 PM IST |  |  | SYN-PERSON-011 |  | None
4 | Execute SFMC stage table creation and SFMC standard table creation to create table in Stage and Standard layer. | " Use the below mentioned Link service with given parameters to create managed table Linked Service Name : LS_DTBR_POOL_ALL_01 Parameters (CHIP Cluster): DatabricksWorkspaceURL : https://syn-dbx-workspace-002.synthetic.example/ DatabricksWorkspaceSecretName :SYN-SECRET-001 AzureKeyVaultURL : https://syn-keyvault-001.synthetic.example/ PoolID : SYN-CLUSTER-002 ClusterVersion : 15.4.x-scala2.12 CatalogName : pr_dlk MaximumWorkerNodes : 8 Create stage and standard tables fromSFMC stage table creation and SFMC standard table creation files using below script. File Location:O:\\SYN-INTERNAL-SHARE\\001 Documentation\2026_3_QTR_Release\SYN-RFC-001_SFMC\'' | SYN-RFC-001 | SYN-PERSON-012 | 2026-08-20 | 2026-08-20 |  |  | 2:30:00 PM IST | 06:30 PM IST |  |  | SYN-PERSON-011 |  | None
POST PRODUCTION
1 | Validate the pipeline deployments | Login into ADF and verify pipeline 1.PL_GMSTR_MBR_OUTREACH_ALL_DLY | SYN-RFC-001 | SYN-PERSON-011 | 2026-08-20 | 2026-08-20 |  |  | 2:30:00 PM IST | 06:30 PM IST |  |  | SYN-PERSON-011 |  | None
2 | Validate the metadata inserts | Enviroment Details : Virtual Machine: SYN-VM-001 Server Name: syn-sqlserver-001.synthetic.example Databricks : SYN-RESOURCE-003 | SYN-RFC-001 | SYN-PERSON-011 | 2026-08-20 | 2026-08-20 |  |  | 2:30:00 PM IST | 06:30 PM IST |  |  | SYN-PERSON-011 |  | None
3 | Validate the stage and standard table is created or not. | Login to Databricks in PROD : SYN-RESOURCE-003 Check the schema created at below location : select * from pr_dlk.stg_mbr.sfmc_member_outreach_email_tracking; select * from pr_std.mbr.sfmc_member_outreach_email_tracking; | SYN-RFC-001 | SYN-PERSON-011 | 2026-08-20 | 2026-08-20 |  |  | 2:30:00 PM IST | 06:30 PM IST |  |  | SYN-PERSON-011 |  | None

## Rollback Execution
| MANDATORY | OPTIONAL | MANDATORY | [12 empty] | OPTIONAL |  | MANDATORY
# | Task | Task Detail | RFC#s | Rollback Execution Team | Rollback Execution Planned Start Date | Rollback Execution Planned End Date | Rollback Execution Actual Start Date | Rollback Execution Actual End Date | Rollback Execution Planned Start Time | Rollback Execution Planned End Time | Rollback Execution Actual Start Time | Rollback Execution Actual End Time | Rollback Execution Task Owner | Rollback Execution Status | Task Dependency | Task Instructions | Communication | Comments: Touch Point Calls/Emails
BACKOUT/ROLLBACK EXECUTION
1 | Revert the IIG tables changes | Databricks : SYN-RESOURCE-003 Describe history pr_dlk_adb.dbo.DATA_FACTORY_PIPELINE_SCHEDULE; Describe history pr_dlk_adb.dbo.ADLS_DELTA_INGESTION_DETAILS; Describe history pr_dlk_adb.dbo.STGDELTA_STDDELTA_INGESTION_DETAILS; Describe history pr_dlk_adb.dbo.DATABRICKS_NOTEBOOK_DETAILS; Describe history pr_dlk_adb.dbo.ALL_FILES_STATIC_INFORMATION; Describe history pr_dlk_adb.dbo.EMAIL_TEMPLATE_CONFIG; Describe history pr_dlk_adb.dbo.DATA_QUALITY_RULES; Restore table pr_dlk_adb.dbo.DATA_FACTORY_PIPELINE_SCHEDULE TO VERSION AS OF <VNO>; Restore table pr_dlk_adb.dbo.FILE_ADLS_INGESTION_DETAILS TO VERSION AS OF <VNO>; Restore table pr_dlk_adb.dbo.STGDELTA_STDDELTA_INGESTION_DETAILS TO VERSION AS OF <VNO>; Restore table pr_dlk_adb.dbo.DATABRICKS_NOTEBOOK_DETAILS TO VERSION AS OF <VNO>; Restore table pr_dlk_adb.dbo.ALL_FILES_STATIC_INFORMATION TO VERSION AS OF <VNO>; Restore table pr_dlk_adb.dbo.EMAIL_TEMPLATE_CONFIG TO VERSION AS OF <VNO>; Restore table pr_dlk_adb.dbo.DATA_QUALITY_RULES TO VERSION AS OF <VNO>; | SYN-RFC-001 | SYN-PERSON-012 | 2026-08-20 | 2026-08-20 |  |  | 2:30:00 PM IST | 06:30 PM IST |  |  | SYN-PERSON-011 |  | None

## Rollback Validation
| MANDATORY | OPTIONAL | MANDATORY | [15 empty] | OPTIONAL |  | MANDATORY
# | Task | Task Detail | RFC#s | Rollback Validation Team | Rollback Validation Planned Start Date | Rollback Validation Planned End Date | Rollback Validation Actual Start Date | Rollback Validation Actual End Date | Rollback Validation Planned Start Time | Rollback Validation Planned End Time | Rollback Validation Actual Start Time | Rollback Validation Actual End Time | Task / App Owner or App Support Resource | Production RFC | Rollback Validation Conditions | Rollback Validation Status | Rollback Validation Done By | Task Dependency | Task Instructions | Communication | Comments: Touch Point Calls/Emails
BACKOUT/ROLLBACK VALIDATION
1 | 1. Validate IIG tables changes | Enviroment Details : Virtual Machine: SYN-VM-001 Server Name: syn-sqlserver-002.synthetic.example select * from ADLS_DELTA_INGESTION_DETAILS where PIPELINE_ID=SYN-PIPE-001; select * from STGDELTA_STDDELTA_INGESTION_DETAILS where PIPELINE_ID=SYN-PIPE-002; select * from DATABRICKS_NOTEBOOK_DETAILS where PIPELINE_ID in (SYN-PIPE-001,SYN-PIPE-002); select * from DATA_QUALITY_RULES where GROUP_ID in (SYN-GRP-001,SYN-GRP-002) order by group_id,sequence_no; select * from DATA_FACTORY_PIPELINE_SCHEDULE where PIPELINE_ID in (SYN-PIPE-001,SYN-PIPE-002,SYN-PIPE-003,SYN-PIPE-004); select * from EMAIL_TEMPLATE_CONFIG where PROCESS_NAME like '%SFMC%' | SYN-RFC-001 | SYN-PERSON-011 | 2026-08-20 | 2026-08-20 |  |  | 2:30:00 PM IST | 06:30 PM IST |  |  | SYN-PERSON-011 |  | None

## Contact List
Contact Name | Deployment Team | Cell Phone | Office | Escalation Point (name/number)
SYN-CONTACT-001 | SYN-CONTACT-002
syn.person.004@synthetic.example
syn.person.003@synthetic.example
SYN-CONTACT-003 | SYN-CONTACT-004
SYN-CONTACT-005
SYN-CONTACT-006 | SYN-CONTACT-007